## Report
Outstanding Issues
Project: London Lane |  |  | Revision: Snag Report |  | Status key | Incomplete
Created by: Insite Team |  |  | Date: 2021-03-15 |  |  | In progress
Complete
No. | Code | Title | Description | Status | Assignees | Locations | Due date | Comments | Created by | Created
1 | 9M4 | Missing tiles | Half the tiles are missing | Complete | - Luke's Electrical | - Bedroom 1 - Ground Floor | 2020-10-30 11:09 | - This needs a new order of tiles test (Insite Team - 2020-10-28 12:15) - Test (Insite Team - 2020-10-28 12:14) | Insite Team | 2020-10-28 11:09
2 | BDP | Damage to door |  | In Progress | - Harry's Fittings | - Kitchen | 2021-03-18 |  | Insite Team | 2021-03-12 09:58
3 | RCN | Sprinkler pipe | Needs additional hanger | In Progress | - Luke's Electrical | - 1st Floor | 2021-08-04 |  | Insite Team | 2021-03-15 20:04
4 | URK | Air conditioning pipes | To be lagged | Incomplete | - Operations Team | - 2nd Floor | 2021-04-15 | - Refer to spec for correct lagging gauge (Insite Team - 2021-03-15 20:02) | Insite Team | 2021-03-15 20:04
5 | 9VF | WCs | Tiles to be grouted | Incomplete | - Operations Team | - Men's WC | 2021-04-29 |  | Insite Team | 2021-03-15 20:06
6 | BM8 | Floor boxes | Carpet to be cut around floor boxes | In Progress | - Site manager | - 2nd Floor | 2021-04-27 | - See site manager for docs (Insite Team - 2021-03-15 20:14) | Insite Team | 2021-03-15 20:15
7 | TO4 | Kitchenette flooring | Prep and lay vinyl tiles | Complete | - Petrov flooring | - Kitchen | 2021-04-28 | - Must be protected as soon as flooring is laid (Insite Team - 2021-03-15 20:16) | Insite Team | 2021-03-15 20:17
8 | Y50 | Prep for carpets | Fill sub floor joints and screw holes | In Progress | - Petrov flooring | - 1st Floor | 2021-04-29 |  | Insite Team | 2021-03-15 20:24
9 | 3E9 | Door frame | Glazing bar to be touched in | In Progress | - Operations Team | - 2nd Floor | 2021-05-28 |  | Insite Team | 2021-03-15 20:30
10 | C09 | Scaffolding | Cut down scaffolding tube | Incomplete | - Tyler's Cladding | - Kitchen | 2020-10-31 10:59 | - Needs two people to remove (Insite Team - 2020-10-28 11:08) | Insite Team | 2021-03-15 20:38